## Sheet1
Project Name | Project Manager | Charge Code | Customer | Project Status | Task Name | Planned Start Date | Planned Finish Date | Planned Duration | Planned Hours | Planned Cost | Planned Resource Cost | Percent Complete | Person | Linked From | Linked To | Actual Start Date | Actual Finish Date | Actual Duration | Actual Hours | Actual Cost | Actual Resource Cost | Remaining Hours | Milestone | Complete | Priority | WBS | Locked | Baseline Duration | Baseline Hours | Baseline Start Date | Baseline Finish Date | Baseline Cost | Notes | Summary | Dependency (From) | Dependency (To) | Tags | Board | To Do list
GrowTradeNet | Lakmal Gamage |  |  | Open | Project Initiation | 2023-05-15 | 2023-05-30 | 11 days |  |  |  | 100 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | True | Medium | 1 | False | [6 empty] | True |  |  |  | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | 1.1 Define Project Scope and Objectives | 2023-05-15 | 2023-05-15 |  |  |  |  | 100 | [9 empty] | 0 Hours | True | True | Medium | 1.1 | False | [6 empty] | False |  |  |  | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | 1.2 Identify Stakeholders and User Groups | 2023-05-15 | 2023-05-15 |  |  |  |  | 100 | [9 empty] | 0 Hours | True | True | Medium | 1.2 | False | [6 empty] | False |  |  | Issue, Risk | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | 1.3 Conduct Feasibility Study | 2023-05-22 | 2023-05-22 |  |  |  |  | 100 | [9 empty] | 0 Hours | True | True | Medium | 1.3 | False | [6 empty] | False |  |  |  | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | 1.4 Develop Project Charter | 2023-05-30 | 2023-05-30 |  |  |  |  | 100 | [9 empty] | 0 Hours | True | True | Medium | 1.4 | False | [6 empty] | False |  |  |  | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | Requirements Gathering and Analysis | 2023-05-10 | 2023-08-21 | 74 days |  |  |  | 100 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] |  |  | 2023-08-10 | [5 empty] | 0 Hours | False | True | Very High | 2 | False | [6 empty] | True |  |  |  | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | 2.1 Gather Functional Requirements from Stakeholders | 2023-05-22 | 2023-05-25 | 4 days |  |  |  | 100 | [9 empty] | 0 Hours | False | True | Very High | 2.1 | False | [6 empty] | False |  |  |  | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | 2.2 Analyze User Stories and Use Cases | 2023-06-27 | 2023-06-28 | 2 days |  |  |  | 100 | [9 empty] | 0 Hours | False | True | Very High | 2.2 | False | [6 empty] | False |  |  |  | Done
GrowTradeNet | Lakmal Gamage |  |  | Open | 2.3 Identify Non-Functional Requirements (Performance, Security, etc.) | 2023-05-10 | 2023-05-18 | 7 days |  |  |  | 100 |  |  |  | 2023-08-10 | 2023-08-10 | 1 day |  |  |  | 0 Hours | False | True | Very High | 2.3 | False | [6 empty] | False |  |  |  | Doing
GrowTradeNet | Lakmal Gamage |  |  | Open | 2.4 Create Requirement Specifications Document | 2023-08-21 | 2023-08-21 | 1 day |  |  |  | 100 |  |  |  | 2023-08-21 | 2023-08-21 | 1 day |  |  |  | 0 Hours | True | True | Very High | 2.4 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | Design and Architecture | 2023-08-09 | 2023-10-20 | 53 days |  |  |  | 17 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] |  |  | 2023-08-09 | [5 empty] | 0 Hours | False | False | Very High | 3 | False | [6 empty] | True |  |  |  | Doing
GrowTradeNet | Lakmal Gamage |  |  | Open | 3.1 Database Design | 2023-10-06 | 2023-10-06 | 1 day |  |  |  | 40 | Viduranga [0%] Lakmal Gamage [0%] |  |  | 2023-08-22 | [5 empty] | 0 Hours | False | False | Very High | 3.1 | False | [6 empty] | False |  |  | Issue, Risk | Doing
GrowTradeNet | Lakmal Gamage |  |  | Open | 3.2 User Interface (UI) Design | 2023-10-20 | 2023-10-20 | 1 day |  |  |  | 90 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] |  |  | 2023-08-23 | [5 empty] | 0 Hours | False | False | Very High | 3.2 | False | [6 empty] | False |  |  | Risk | Doing
GrowTradeNet | Lakmal Gamage |  |  | Open | 3.3 Application Architecture Design | 2023-08-09 | 2023-08-09 | 1 day |  |  |  | 40 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] |  |  | 2023-08-09 | [5 empty] | 0 Hours | False | False | Very High | 3.3 | False | [6 empty] | False |  |  |  | Doing
GrowTradeNet | Lakmal Gamage |  |  | Open | 3.4 API Design and Documentation | 2023-10-10 | 2023-10-18 | 7 days |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 3.4 | False | [6 empty] | False |  |  | Risk | Doing
GrowTradeNet | Lakmal Gamage |  |  | Open | Frontend Development | 2023-08-24 | 2023-10-04 | 30 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Very High | 4 | False | [6 empty] | True |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.1 Create Farmers Module UI | 2023-10-02 | 2023-10-04 | 3 days |  |  |  | 0 | Viduranga [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.1 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.2 Create Fertilizer Sellers Module UI | 2023-08-29 | 2023-08-29 | 1 day |  |  |  | 0 | Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.2 | False | [6 empty] | False |  |  | Change | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.3 Create Exporters Module UI | 2023-09-20 | 2023-09-27 | 6 days |  |  |  | 0 | Thilan [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.3 | False | [6 empty] | False |  |  | Change, Risk | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.4 Create Wholesale Persons Module UI | 2023-09-08 | 2023-09-08 | 1 day |  |  |  | 0 | Shalani [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.4 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.5 Implement User Authentication and Authorization | 2023-08-24 | 2023-08-24 | 1 day |  |  |  | 0 | Viduranga [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.5 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.6 Implement Crop Recommendation Feature | 2023-08-24 | 2023-08-24 | 1 day |  |  |  | 0 | Viduranga [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.6 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.7 Implement Inbox for Communication | 2023-08-24 | 2023-08-24 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.7 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.8 Implement Ads Viewing and Posting Features | 2023-08-24 | 2023-08-24 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 4.8 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 4.9 Implement Weather Reports Feature | 2023-09-12 | 2023-09-12 | 1 day |  |  |  | 0 | Viduranga [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | True | False | Very High | 4.9 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | Backend Development | 2023-10-25 | 2023-11-16 | 17 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Critical | 5 | False | [6 empty] | True |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 5.1 Set up Server and Hosting Environment | 2023-11-01 | 2023-11-01 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 5.1 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 5.2 Implement User Registration and Login Functionality | 2023-11-03 | 2023-11-03 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 5.2 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 5.3 Develop APIs for Crop Recommendation | 2023-11-08 | 2023-11-08 | 1 day |  |  |  | 0 | Viduranga [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 5.3 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 5.4 Implement Inbox Communication Functionality | 2023-11-14 | 2023-11-14 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 5.4 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 5.5 Create APIs for Ads Posting and Viewing | 2023-11-16 | 2023-11-16 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 5.5 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 5.6 Integrate Google Maps API for Location-based Features | 2023-10-25 | 2023-10-30 | 4 days |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 5.6 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | User Modules Development | 2023-11-17 | 2023-12-25 | 27 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Very High | 6 | False | [6 empty] | True |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.1 Farmers Module | 2023-11-17 | 2023-11-17 |  |  |  |  | 0 | Viduranga [0%] | [8 empty] | 0 Hours | True | False | Very High | 6.1 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.1.1 Implement Farmer Registration | 2023-11-20 | 2023-11-20 | 1 day |  |  |  | 0 | Viduranga [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.2 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.1.2 Develop Crop Recommendation Algorithm | 2023-11-22 | 2023-11-22 | 1 day |  |  |  | 0 | Viduranga [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.3 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.1.3 Create Ad Posting for Crops | 2023-11-24 | 2023-11-24 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.4 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.1.4 Integrate Weather Report API | 2023-11-28 | 2023-11-28 | 1 day |  |  |  | 0 | Viduranga [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.5 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.2 Fertilizer Sellers Module | 2023-11-30 | 2023-11-30 | 1 day |  |  |  | 0 | Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.6 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.2.1 Implement Seller Registration | 2023-12-01 | 2023-12-01 | 1 day |  |  |  | 0 | Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.7 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.2.2 Develop Ad Posting for Fertilizer Products | 2023-12-04 | 2023-12-04 | 1 day |  |  |  | 0 | Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.8 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.2.3 Add Store Information and Product Listings | 2023-12-05 | 2023-12-05 | 1 day |  |  |  | 0 | Viduranga [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.9 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.3 Exporters Module | 2023-12-08 | 2023-12-08 | 1 day |  |  |  | 0 | Thilan [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.10 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.3.1 Implement Exporter Registration | 2023-12-12 | 2023-12-12 | 1 day |  |  |  | 0 | Thilan [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.11 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.3.2 Create Ad Posting for Export Needs | 2023-12-14 | 2023-12-14 | 1 day |  |  |  | 0 | Thilan [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.12 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.3.3 Implement Searching and Locating Farmers | 2023-12-18 | 2023-12-18 | 1 day |  |  |  | 0 | Shalani [0%] Thilan [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.13 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.4 Wholesale Persons Module | 2023-12-20 | 2023-12-20 | 1 day |  |  |  | 0 | Shalani [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.14 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.4.1 Implement Wholesale Person Registration | 2023-12-21 | 2023-12-21 | 1 day |  |  |  | 0 | Shalani [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.15 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.4.2 Create Ad Posting for Wholesale Needs | 2023-12-22 | 2023-12-22 | 1 day |  |  |  | 0 | Shalani [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.16 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 6.4.3 Implement Searching and Locating Farmers | 2023-12-25 | 2023-12-25 | 1 day |  |  |  | 0 | Shalani [0%] Thilan [0%] | [8 empty] | 0 Hours | False | False | Very High | 6.17 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | System Admin Module | 2023-12-26 | 2024-01-05 | 9 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Very High | 7 | False | [6 empty] | True |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.1 Implement Admin Dashboard | 2023-12-26 | 2023-12-26 | 1 day |  |  |  | 0 | Shalani [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.1 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.2 User Account Management Functionality | 2023-12-27 | 2023-12-27 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.2 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.3 Send Notifications and Announcements to Users | 2023-12-28 | 2023-12-28 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.3 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.4 Enforce Security Measures and Access Controls | 2023-12-29 | 2023-12-29 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.4 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.5 Set Up System Logs and Audit Trails | 2024-01-01 | 2024-01-01 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.5 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.6 Manage Application Settings | 2024-01-02 | 2024-01-02 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.6 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.7 Implement Localization and Internationalization Support | 2024-01-03 | 2024-01-03 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.7 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.8 Handle User Support Tickets | 2024-01-04 | 2024-01-04 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.8 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 7.9 Monitor System Health and Performance | 2024-01-05 | 2024-01-05 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 7.9 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | Testing and Quality Assurance | 2024-01-08 | 2024-01-15 | 6 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Very High | 8 | False | [6 empty] | True |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 8.1 Unit Testing of Individual Components | 2024-01-08 | 2024-01-08 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 8.1 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 8.2 Integration Testing of Modules | 2024-01-09 | 2024-01-09 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 8.2 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 8.3 User Acceptance Testing (UAT) | 2024-01-10 | 2024-01-10 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 8.3 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 8.4 Performance Testing | 2024-01-11 | 2024-01-11 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 8.4 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 8.5 Security Testing | 2024-01-12 | 2024-01-12 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 8.5 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 8.6 Bug Fixes and Issue Resolution | 2024-01-15 | 2024-01-15 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Very High | 8.6 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | Documentation and Training | 2024-01-16 | 2024-01-18 | 3 days |  |  |  | 0 | [9 empty] | 0 Hours | False | False | Medium | 9 | False | [6 empty] | True |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 9.1 Prepare Technical Documentation | 2024-01-16 | 2024-01-16 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Medium | 9.1 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 9.2 Create User Manuals and Guides | 2024-01-17 | 2024-01-17 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Medium | 9.2 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 9.3 Conduct Training for Users and Administrators | 2024-01-18 | 2024-01-18 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Medium | 9.3 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | Deployment and Post-Deployment Support | 2024-01-19 | 2024-01-24 | 4 days |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 10 | False | [6 empty] | True |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 10.1 Prepare Application for Production Deployment | 2024-01-19 | 2024-01-19 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 10.1 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 10.2 Deploy Application on Hosting Server | 2024-01-22 | 2024-01-22 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 10.2 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 10.3 Monitor Application After Deployment | 2024-01-23 | 2024-01-23 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 10.3 | False | [6 empty] | False |  |  |  | To Do
GrowTradeNet | Lakmal Gamage |  |  | Open | 10.4 Provide Ongoing Support and Maintenance | 2024-01-24 | 2024-01-24 | 1 day |  |  |  | 0 | Viduranga [0%] Shalani [0%] Thilan [0%] Lakmal Gamage [0%] | [8 empty] | 0 Hours | False | False | Critical | 10.4 | False | [6 empty] | False |  |  |  | To Do